ASO SIGNATURE

Alteration Partner Implementation — Task List

# 1. Tasks

| # | Task | Where it goes | ETA |
| --- | --- | --- | --- |
| 1 | Write down the fault definitions: ASO/designer fault = did not produce to the customer's confirmed spec (includes material grade/quality, since grades are known upfront); Customer fault = matches confirmed spec, but the submitted measurements were wrong. | Ese Policy Doc (Refund & Return Policy) + internal fault-classification guide | 21st |
| 2 | Write the one-off limit into policy: Aso covers one alteration per order for its own fault; any further issue on that order is not covered under this provision. | Policy Doc (Refund & Return Policy) | 21st |
| 3 | Add a 7-day reporting window for alteration claims, matching the existing Refund Policy window. | Terms & Conditions + Refund & Return Policy | 21st |
| 4 | Require photos plus a measurement comparison before a case is confirmed as ASO-fault; build this into the request flow. | Alteration Request Form / Tech | 21st |
| 5 | Build a cost plan and price sheet for partners, broken down by fix-type, so the ASO-pays path has a cap. | Internal Ops / Finance | 22nd |
| 6 | Create a partner vetting process and checklist — minimum quality bar before a tailor is added to the list. | Internal Ops / Partner Onboarding | 22nd |
| 7 | Make a payment plan for alteration partners and push it to them. | Partner Sourcing (Ese) | 22nd |
| 8 | Scout alteration partners — expand target list to diaspora hubs: London, Bristol, Vancouver, Paris, and other key shipping destinations. | Partner Sourcing (Walid + Ese) |  |
| 9 | Build a partner status list: Contacted – No Response / Positive / Negative / Canceled. | Alteration Support Tracker (internal) | 21st |
| 10 | Add each partner's prices and any side conditions to the list. | Alteration Support Tracker (internal) | 21st |
| 11 | Build the support-component tailor locator: customer enters a location, component lists the nearest vetted partners. | Tech | 23rd |

# 2. What Needs to Change in the Policy Doc

## Refund & Return Policy

- Under ASO Fault: state the definition (garment does not match the measurements confirmed at checkout, including material grade/quality) and the one-off limit (“Aso Signature covers one alteration per order due to a production error; subsequent issues on that order are not covered under this provision”).

- Under ASO Fault: note that photo evidence and a measurement comparison are required before a claim is confirmed as ASO's fault.

- Under Customer Fault: state that ASO provides a suggested list of vetted alteration partners, the customer pays for the work, and the partner — not Aso Signature — is responsible for the outcome of that work once engaged.

- Add the 7-day reporting window for alteration claims, matching the window already used elsewhere in this policy.

## Terms & Conditions

- Add the 7-day alteration reporting window alongside the existing returns/refunds language in Section 8.

- In Section 11 (Limitation of Liability), add a line clarifying that Aso's one-off fault coverage does not extend to repeat issues on the same order, or to work carried out by a partner after handoff — so this section doesn't read as contradicting the new alteration process.

## Aso Fit Assurance Policy (currently unpublished)

- This is the natural home for the full alteration process once it's finalized — fault definitions, the one-off limit, the 7-day window, the verification requirement, and the customer-fault handoff — rather than folding all of it into the Refund Policy.